## Buck 9-Week Gantt Chart
BUCK: FINANCE & EXPENSES TRACKER
Software Project Management Plan (SPMP) — 9-Week Master Gantt Schedule
[7 empty] | Weeks 1–3: Planning, Architecture & DB Setup |  |  | Weeks 4–6: Web/Mobile Core Dev & AI Integration |  |  | Weeks 7–9: Realtime Sync, UAT, Security & Defense
WBS ID | Task / Milestone Description | Assigned Lead | Start | End | Duration | Status | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
PH-01 | Phase 1: Project Initiation & Requirements Baseline | Team | W1 | W2 | 2 wks | Completed
1.1 | • Project Scoping, IEEE 1058 SPMP & Stakeholder Alignment | J. Gamboa | W1 | W1 | 1 wk | Completed
1.2 | • SRS Document Finalization (40-Item Requirements Matrix) | M. Mora | W1 | W2 | 2 wks | Completed
PH-02 | Phase 2: UI/UX Design System & Architecture Specifications | Team | W2 | W3 | 2 wks | Completed
2.1 | • High-Fidelity Figma Wireframes & Mobile Viewfinder Overlay | C. Rivera | W2 | W3 | 2 wks | Completed
2.2 | • Software Design Document (SDD V1.0) & 3NF ERD Modeling | J. Gamboa | W3 | W3 | 1 wk | Completed
PH-03 | Phase 3: Database & Cloud Infrastructure Setup | Team | W3 | W4 | 2 wks | Completed
3.1 | • Supabase PostgreSQL 15 Setup, DDL & Kernel RLS Policies | J. Gamboa | W3 | W4 | 2 wks | Completed
3.2 | • GoTrue JWT Auth & Stored Procedure (transfer_funds_atomic) | J. Gamboa | W4 | W4 | 1 wk | In Progress
PH-04 | Phase 4: Frontend Application Core Development | Team | W4 | W6 | 3 wks | In Progress
4.1 | • Next.js 14 Web App: Multi-Wallet Ledger & Budget Gauges | C. Rivera | W4 | W6 | 3 wks | In Progress
4.2 | • Flutter Mobile App: Native Views & Local SQLite Caching | J. Pariño | W4 | W6 | 3 wks | In Progress
PH-05 | Phase 5: AI & Machine Learning Microservice Integration | Team | W5 | W7 | 3 wks | In Progress
5.1 | • Mobile On-Device Edge Vision OCR & 12% EVAT Isolation | J. Pariño | W5 | W6 | 2 wks | In Progress
5.2 | • FastAPI Python: Zero-Shot 17-Category NLP Classifier | J. Gamboa | W5 | W6 | 2 wks | In Progress
5.3 | • Prophet Time-Series Forecaster (80% CI) & 2-Sentence Advisor | J. Gamboa | W6 | W7 | 2 wks | In Progress
PH-06 | Phase 6: End-to-End System Integration & Real-Time Sync | Team | W7 | W8 | 2 wks | Scheduled
6.1 | • Supabase Realtime (WSS) Cross-Platform Sync & CDC Events | J. Gamboa | W7 | W8 | 2 wks | Scheduled
6.2 | • Alpha Build Deployment & Dogfooding Milestone | Team | W7 | W8 | 2 wks | Scheduled
PH-07 | Phase 7: Quality Assurance, UAT & Security Auditing | Team | W8 | W9 | 2 wks | Scheduled
7.1 | • Formal Requirements Verification (40-Item Traceability Matrix) | M. Mora | W8 | W8 | 1 wk | Scheduled
7.2 | • Security Penetration Testing, PII Audit & OCR Benchmarks | M. Mora | W8 | W8 | 1 wk | Scheduled
7.3 | • Defect Remediation & Release Candidate (RC) Hardening | Team | W8 | W9 | 2 wks | Scheduled
PH-08 | Phase 8: Production Deployment, Defense & Final Handover | Team | W9 | W9 | 1 wk | Scheduled
8.1 | • Cloud Deployment (Vercel Edge & Supabase Production) | J. Gamboa | W9 | W9 | 1 wk | Scheduled
8.2 | • Academic Project Defense, Documentation Handover & Closeout | All Members | W9 | W9 | 1 wk | Scheduled
Status & Gantt Bar Legend:
Completed
In Progress
Scheduled / Upcoming